## SPRINT_BACKLOG
SPRINT [NUMBER] BACKLOG

ID	User Story	Tasks	Owner	Status	Estimated effort	Day 1	Day 2	Day 3	Day 4	Day 5	Day 6	Day 7
SP001	As an user I need to be able to list Users and Accounts.	Code “list files”: Select folder, define a structure, sort and display	Jluque	Completed	20	8
		Create empty menus	Jluque	Completed			8
		Demo, show list files functionalities	Jluque	Completed				2	2
	As an user I need to be able to Request Chequebooks.	Code Insert file: define folder, check duplicated exception, store	Jluque	Completed	20			6	3
		Prepare and execute demo	Jluque	Completed					3	8
SP002	As an Admin User, I should be able to list and manage the different entitites of the project.	Code Delete file: define folder, watch checked exceptions.	Jluque	Completed	10	8
		other exceptions	jluque	Completed			2
	As an user I need to be able to search for data on transactions	Code Search: define folder, check letter case	jluque	Completed	22		6	2
		Prepare a complete demo	jluque	Completed				4	4
		Complete any changes required from Demo	jluque	Completed					4	2
SP003	As an user I need to be able to do banking transaction such as: Deposit, withdrawal and Transfer	Code “list files”: Select folder, define a structure, sort and display	Jluque	Completed	20	8
		Create empty menus	Jluque	Completed			8
		Demo, show list files functionalities	Jluque	Completed				2	2
	As an user I need to be able to see all the user profile information where all the personal data is shown and the Account list.	Code Insert file: define folder, check duplicated exception, store	Jluque	Completed	20			6	3
		Prepare and execute demo	Jluque	Completed					3	8
SP004	Administrators should be able to accept or rejected a request	Code Delete file: define folder, watch checked exceptions.	Jluque	Completed	10	8
		other exceptions	jluque	Completed			2
	registered to the portal. Also, administrators should be able to grant access to transactions and activate or deactivate users or accounts.	Code Search: define folder, check letter case	jluque	Completed	22		6	2
		Prepare a complete demo	jluque	Completed				4	4
		Complete any changes required from Demo	jluque	Completed					4	2
					144	32	32	24	24	18	0	0

## PROJECT_DETAILS
PROJECT NUMBER	PR001
PROJECT NAME	LockedMe
PROJECT MANAGER	Javier Luque
DATE	02/15/22
VERSION	0.1